## Slide 1
Improving Documentation of Infant Feeding Assessments
JHBMC Maternal Child Health
Objective / Goal / Scope:
The % total shifts with feeding assessment documentation meeting expectations will meet or exceed 95% benchmark by July 2021
% shifts with Infant feeding times documented per order will meet or exceed 95% benchmark by July 21
% shifts with Latch scores and feeding readiness documented will meet or exceed 95% benchmark by July 2021
% shifts with Stool assessment documented will meet or exceed 95% benchmark by July 21
Key Metrics:
% shifts with feeding assessment documentation meeting expectations
Scope: Limited to maternal and infant patient charts for deliveries that occur in JHBMC and remain admitted throughout their postpartum/newborn care in A2W and NBN
Core Team Members:
Cusp Team
Unit Management
Pediatric Providers, FNPs, and PAs
Background / Problem Statement:
Nursing documentation of infant Feeding, latch documentation and score, and stool assessment do not meet regulatory or best practice standards 20-100% of nursing shifts potentially leading to increased incidences of formula supplementation and delay of discharge
JHM Strategic Priority to Improve the Quality and Affordability of Health Care
Define: “Characterize the Current State”
Measure: “Baseline the Process and Current Trends”
Analyze: “Identifying Problem Root Causes”
Improve: “Identifying, Prioritizing and Piloting Logical Interventions”
A3 Owner : Katharine Giancola MSN RN IBCLC C-EFM, Susan Aronson BSN RN-C C-EFM
Revision Date: 7/28/2021
Control: “Structure and Process Controls to Sustain Improvements”
Chart: % shifts with documentation
| 43739 | 43770 | 43800 | 44013 | 44044 | 44075 | 44105 | 44136 | 44166 | 44197 | 44228 | 44256 | 44287 | 44317 | 44348
Feeding Times | 0.74783 | 0.85593 | 0.70992 | 0.83654 | 0.80342 | 0.82759 | 0.66087 | 0.83178 | 0.86275 | 0.83962 | 0.84694 | 0.85124 | 0.9187 | 0.8374 | 0.93913
Latch | 0.084211 | 0.21053 | 0.23276 | 0.73529 | 0.63462 | 0.55752 | 0.40952 | 0.72549 | 0.70707 | 0.62651 | 0.94898 | 0.94175 | 0.88596 | 0.78992 | 0.91743
Stool | 0.043478 | 0.067797 | 0.076336 | 0.038462 | 0.68376 | 0.66379 | 0.6 | 0.78505 | 0.73529 | 0.89623 | 0.95918 | 0.96694 | 0.88618 | 0.88618 | 0.95652
Work in Progress
Chart audits conducted monthly by CUSP team
  Individualized feedback for charting deficits
  Recognition follow-up for “perfect” charts
Newborn Nursery workgroup
  Publish integrated policies for Glucose, newborn care, and thermoregulation of the late preterm in progress
  Develop and provide staff education completed
  Set target date for NBN implementation in progress
Next Steps
Recruit additional CUSP team members
Collaborate with Education and Lactation teams for staff education
Audit charts for non-NICU late preterm infants